## Sheet1
Requirement Description	Assigned To (Member of the team)	Status(Draft, Accepted, Programmed, Tested, Verified, etc)	Target Iteration (how many times are you visiting this requiremet to work it. For example 1/2/3/4 iteration)	Priority(Must Have, Should Have, Nice to Have)	Date Assigned	Approx Date to be completed

Finding a face detection algorithm	Aditya Jadhav	Verified	2	Must Have	05/02/18	10/01/18
Detecting Faces	Abhishek Jadhav	Verified	2	Must Have	07/01/18	07/02/18
Recognising Faces	Abhishek Jadhav	Verified	2	Must Have	20/01/18	20/02/18
Database Schema	Aditya Jadhav	Verified	2	Must Have	08/01/18	28/01/18
Front End Teacher UI web app	Aditya Jadhav	Verified	2	Must Have	09/02/18	09/03/18
Front End Student UI web app	Aditya Jadhav	Verified	2	Should Have	15/02/18	15/03/18
Accuracy of recognition algorithm	Abhishek Jadhav	Verified	2	Must Have	16/02/18	06/03/18
Connection of python script with DB	Abhishek Jadhav	Verified	2	Must Have	22/02/18	15/03/18
Adding timetable to database	Aditya Jadhav	Verified	1	Must Have	25/02/18	10/03/18
Integrating timetable and script	Abhishek Jadhav	Verified	2	Must Have	08/03/18	30/03/18